## DILG
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Lack of access to Potable Water | Provision of Potable Water Supply | Calango and Mayabon, Zamboanguita and nearby barangays | 500 Households | Increased no of households with access to potable water | DILG | 5479006 | Submission of documentary requirements and financial counterpart by the city/municipality | Ongoing
| Provision of Potable Water Supply (Level 2: (Spring water source with transmission and distribution lines, spring & intake tanks, communal faucet, air release & blow-off valves) | Mayabon, Zamboanguita and nearby barangays | 500 Households | Promotion of financial literacy and strengthen community/ neighborhood family values | DILG | 9997000 |  | Ongoing
Lack of knowledge on effective and sustainable savings | Community Manage Savings and Credit Association (COMSCA) | Influenced barangays in Guihulngan and Zamboanguita | Vulnerable families | Promotion of financial literacy and strengthen community/ neighborhood family values | World Vision and DILG | 4, 000.00 per group for the provision of COMSCA Kit, | Identification and mobilization of beneficiaries by the city/municipality | 2019-2020 1-year (fully organized)
RCSP (Basic Services) Convergence | Dagyawan sa Barangay thru Talakayan ng Mamayan cum Serbisyo Caravan | Guihulngan City, Canlaon City, Zamboanguita, Siaton, Santa Catalena, Valencia | Affected CTG Barangays | Database of consolidated issues and recommendations; List of benes for the Services provided | DILG, DSWD, DOH,DOLE, NCIP,DOE, DAR, DA, NICA, NHA,HUDC, NEDA | TBD | NOTF and C/MTF | 3rd and 4th Quarter | To establish a Working Framework
Absence of monitoring and evaluation mechanism | SubayBayan, DevLive, Tracking of Accomplishment Reports (Liquidation) |  |  | Institutionalization of Feedback Mechanism and Participatory Governance; Project Sustainbility | DILG | No funds needed | LGU | 4th Quarter | To finalize consolidated Platform
| Insufficient/dilapidated road | Trinidad, Guihulgan City | 1,173 Households | Access to Main Road Networks and improved transportation system | DILG | 1000000 | Submission of documentary requirements and financial counterpart by the city/municipality | 2020
|  | Binobohan and Tacpao, Guihulgan City | 648 Households | Access to Main Road Networks and improved transportation system | DILG | 1000000 | Submission of documentary requirements and financial counterpart by the city/municipality | 2020
|  | Sandayao, Guihulgan City | 744 Households | Access to Main Road Networks and improved transportation system | DILG | 1000000 | Submission of documentary requirements and financial counterpart by the city/municipality | 2020
|  | Imelda, Guihulgan City | 241 Households | Access to Main Road Networks and improved transportation system | DILG | 1000000 | Submission of documentary requirements and financial counterpart by the city/municipality | 2020
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DOE,NEA
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Lack of access to electricity (On and Off Grid) | 1. National Intensification of Household Electrification | Brgy. Binobohan Guihulngan, Bgry. Sandayao, Guihulngan, Bgry. Imelda, Guihulngan, Bgry. Tacpao, Guihulngan, Bgry. Humay-humay, Guihulngan, Bgry. Trinidad, Guihulngan, Bgry. San Pedro, Sta. Catalina, Bgry. Tayak, Siaton | Households ( subject for rapid rural appraisal and site validation) | Energized households/ improved power supply and improved living condition | DOE, NEA | Regular Funds | Logistics/ mobility/security /labor conterpart | 2019-2022 | To conduct IEC campaign with LGUs, Training and capacity building of host LGUs and beneficiaries
2. Off-grid/ Micro -grid Electrification using Renewable Energy Systems (Solar, Hydro, Biomass
3. ER 1-94 ( Electrification)
Lack of Schools/ Learning Center and access to other basic services | 1. ER 1-94 ( Education, Health, and Livelihood) | Brgy. Dobdob, Valencia, Bgry. Calango, Zambonguita, Bgry. Mayabon, Zamboanguita, Bgry. San Pedro, Sta. Catalina, Bgry. Bayug, Canlaon City, Bgry. Lumapao, Canlaon City, Brgy. Binobohan Guihulngan, Bgry. Sandayao, Guihulngan, Bgry. Imelda, Guihulngan, Bgry. Tacpao, Guihulngan, Bgry. Humay-humay, Guihulngan, Bgry. Trinidad, Guihulngan, Bgry. Hinakpan, Guihulngan, Bgry. Planas, Guihulngan, Bgry. Tayak, Siaton | Barangays (subject for validation and approval of provincial and municipal government | 1. Access to education, health services | DOE, NEA | Regular Funds | Logistics/mobility/security/labor counterpart | 2019-2022 | To conduct IEC campaign with LGUs, Training and capacity building of host LGUs and beneficiaries
2. Increased income or livelihood opportunities
3. Improved literacy
Lack of access to electricity (On and Off Grid) | 1. National Intensification of Household Electrification | Brgy. Binobohan Guihulngan, Bgry. Sandayao, Guihulngan, Bgry. Imelda, Guihulngan, Bgry. Tacpao, Guihulngan, Bgry. Humay-humay, Guihulngan, Bgry. Trinidad, Guihulngan, Bgry. San Pedro, Sta. Catalina, Bgry. Tayak, Siaton | Households ( subject for rapid rural appraisal and site validation) | Energized households/ improved power supply and improved living condition | DOE, NEA | Funding | Logistics/ mobility/security /labor conterpart | 2019-2022 | To conduct IEC campaign with LGUs, Training and capacity building of host LGUs and beneficiaries
2. Off-grid/ Micro -grid Electrification using Renewable Energy Systems (Solar, Hydro, Biomass
3. ER 1-94 ( Electrification)
Lack of Schools/ Learning Center and access to other basic services | 1. ER 1-94 ( Education, Health, and Livelihood) | Brgy. Dobdob, Valencia, Bgry. Calango, Zambonguita, Bgry. Mayabon, Zamboanguita, Bgry. San Pedro, Sta. Catalina, Bgry. Bayug, Canlaon City, Bgry. Lumapao, Canlaon City, Brgy. Binobohan Guihulngan, Bgry. Sandayao, Guihulngan, Bgry. Imelda, Guihulngan, Bgry. Tacpao, Guihulngan, Bgry. Humay-humay, Guihulngan, Bgry. Trinidad, Guihulngan, Bgry. Hinakpan, Guihulngan, Bgry. Planas, Guihulngan, Bgry. Tayak, Siaton | Barangays (subject for validation and approval of provincial and municipal government | 1. Access to education, health services | DOE, LGUs | Funding | Logistics/mobility/security/labor counterpart | 2019-2022 | To conduct IEC campaign with LGUs, Training and capacity building of host LGUs and beneficiaries
2. Increased income or livelihood opportunities
3. Improved literacy
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## NHA, HUDCC
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Lack of housing and Land Tenure | Coordination meeting with LCEs | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | MOA with SP Resolution | NHA |  | LGU | 2019-2020 | NHA Funded Projects
| Site visit or occular inspection of possible sites for housing | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | Titled land under the LGU | NHA |  |  | 2019-2020
| Identification of beneficiaries | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | Masterlist of beneficiaries | NHA |  | LGU | 2020
| Packaging of housing program | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | Project proposal or project package | NHA |  | LGU | 2021
| Implementation of housing projects | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | Completed housing units | NHA |  | LGU | 2022 onwards | NHA Funded Projects
| Creation of local housing board | Canlaon City, Siaton, Guihulngan City, Valencia and Zamboanguita | All identified barangays | Ordinance or executive order | HUDCC |  | NHA or LGU | 2019-2020
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DENR
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
| Continued implementation of NGP and hiring of Bantay Gubat Forest/Protection Officer | Canlaon City, Siaton, Guihulngan City, Valencia, Zamboanguita, Sta. Catalina | People's Organization/ Area Planted or Maintained/FPO Hired |  | DENR | Regular Funds | PNP, AFP, Task Force Balik-Loob Members | 2019-2020 | ongoing
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## NEDA
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
| ELCAC Concerns included in the updating of RDP | All areas | All beneficiaries | Updated RDP | NEDA/RDC | RDC Funds | Inputs from agencies | 2019
| ELCAC Project Monitoring | ELCAC/JTF Project Areas | All beneficiaries | Regular monitoring | NEDA | RPMC Funds | Participation of RPMC Members
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DOH
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Delayed delivery of health services | Implementation of zero open defecation project | Canlaon City, Siaton, Guihulngan City, Valencia, Zamboanguita, Sta. Catalina | Community | Sanitary toilet trained sanitary inspector per municipality water testing equipment per municipality | DOH 7 |  | LGU: manpower/labor | 2020 | Proposed in the 2020 budget proposal
| Provision of Barangay Health Stations | Barangay Tayak, Siaton, Hinakpan, Guihulngan City, Lumapao, Canlaon City | Community | BHS | DOH 7 |  | LGU: security/peace and order | 2019-2020 | Most of the identified barangays have existing BHS but lacking complimentary personnel c/o LGU
| Provision of Human Resources for Health | Target municipalities | Community
Canlaon City - Nurse - 7, Midwife - 4, PHA - 1
Guihulngan City - Nurse - 13, Midwife - 3, PHA - 2, Medtech - 1
Siaton - Nurse - 14, PHA - 1, Midwife - 3, MT - 1
Sta. Catalina - Nurse - 12, PHA - 1, Midwife - 3, MT - 1
Valencia - Nurse - 11, PHA - 1, Midwife - 3, MT - 1, Dietician - 1
Zamboanguita - Nurse - 9, PHA - 1, Midwife - 2, MT - 1, Dietician - 1
| Provision of medical assistance program (MAP) | Per Congressional District |  |  |  |  | Congressional or LCE Endorsement | 2019-2020
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DAR
Issues and Concerns to be Addressed | Program/Project/Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Land Titling application, issuance and distribution | Acquisition, Distribution and Installation of ARBs | Planas, Guihulngan | 15 ARBs | acquired, issued and Installation of ARBs | DAR | Mobilization-P 20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 2019 2nd Sem.
ARBs are not aware on the status of their land | Acquisition, Distribution and Installatiuon of ARBs | 9 has. Sandayao, Guihulngan | 4 ARBs | Distribution & Installation of ARBs | DAR | Mobilization-P 20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 2019 2nd Sem.
Subdivision of Collective into Individual CLOAs | Subdivision of Distributed Lands to ARBs | 23 has at Sandayao, Guihulngan | 29 ARBs | Individual CLOAs | DAR | Mobilization-P 20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 2019 2nd Sem.
Tenant-farmers not aware of their status | Info on CARP | 24 has at Sandayao, Guihulngan | 11 Tenant -farmers | informed on their Land Status | DAR | Mobilization-P 20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 2019 2nd Sem.
ARBs land already surveyed, No CLOAs received | Land Survey and Distribution of individual CLOAs | 23 has. At Sandayao, Guihulngan | 13 ARBs | Surveyed and CLOAs distributed | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Distributed land surveyed but no CLOAs received | Approval of Survey, CLOA generation | 18 has at Sandayao, Guihulngan | 9 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Subdivision of Collective CLOAs | Land Survey | 9 has. Sandayao, Guihulngan | 16 ARBs | CLOA subdivided | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Subdivision of Collective CLOAs | Collective CLOA subdivision | 24 has at Sandayao, Guihulngan | 6 ARBs | CLOA subdivided | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Subdivision of Collective CLOA and Issuance of Individual CLOAs | Land Survey and Distribution of individual CLOAs | 15 has at Sandayao, Guihulngan | 13 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Subdivision of Collective CLOA | Land Survey and Distribution of individual CLOAs | 8 has at Sandayao, Guihulngan | 9 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Land related issues,Re: Survey and Distribution of Individual CLOAs | Survey of Collective CLOAs and distribution of Individual CLOAs | Samac, Bagtic and Luyang, all of MABINAY | 20 ARBs | CLOAs subdivided and distri bution of individual CLOAs | DAR | Mobilization-P 20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 2019 2nd Sem.
Land Titling application, issuance and distribution | Acquisition, Distribution and Installation of ARBs | Planas, Guihulngan | 15 ARBs | acquired, issued and Installation of ARBs | DAR | Mobilization P20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 1st Sem. CY 2020
ARBs are not aware on the status of their land | Acquisition, Distribution and Installation of ARBs | 9 has. Sandayao, Guihulngan | 4 ARBs | Distribution & Installation of ARBs | DAR | Mobilization P20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 1st Sem. CY 2020
Subdivision of Collective CLOAs into Individual CLOAs | Subdivision of Distributed Lands to ARBs | 23 has at Sandayao, Guihulngan | 29 ARBs | Individual CLOAs | DAR | Mobilization P20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 1st Sem. CY 2020
Tenant-farmers not aware of their status | Information on CARP Implementation | 24 has at Sandayao, Guihulngan | 11 Tenant -farmers | informed on their Land Status | DAR | Mobilization P20,000.00 | Assistance from PNP, AFP, BLGU and MLGU | 1st Sem. CY 2020
ARBs are not aware on the status of their land | Land Survey and Distribution of individual CLOAs | 23 has at Sandayao, Guihulngan |  |  |  | Mobilization P20,000.00 |  | 1st Sem. CY 2020
ARBs land already surveyed, No CLOAs received | Land Survey and Distribution of individual CLOAs | 23 has. At Sandayao, Guihulngan | 13 ARBs | Surveyed and CLOAs distributed | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Subdivision of Collective CLOAs | Land Survey | 9 has. Sandayao, Guihulngan | 16ARBs | CLOA subdivided | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Subdivision of Collective CLOAs | Collective CLOA subdivision | 24 has at Sandayao, Guihulngan | 6ARBs | CLOA subdivided | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Distributed land surveyed but no CLOAs received | Approval of Survey, CLOA generation | 18 has at Sandayao, Guihulngan | 9 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Subdivision of Collective CLOA and Issuance of Individual CLOAs | Land Survey and Distribution of individual CLOAs | 15 has at Sandayao, Guihulngan | 13 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Subdivision of Collective CLOA | Land Survey and Distribution of individual CLOAs | 8 has at Sandayao, Guihulngan | 9 ARBs | CLOA subdivided and issued Individual CLOAS | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
Land related issues, Re: Survey and Distribution of Individual CLOAs | Survey of Collective CLOAs and distribution of Individual CLOAs | Samac, Bagtic and Luyang, all of MABINAY | 20 ARBs | CLOAs subdivided and distri bution of individual CLOAs | DAR | Mobilization P20,000.00 | Assistance from PNP,AFP, BLGU, MLGU | 1st Sem. CY 2020
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DA_PROVINCE
Issues and Concerns to be Addressed | Program/Project/ Activity | Target Area | Target Beneficiaries | Expected Results/ Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
No Livelihood Assistance | Livestock and Poultry Program |  | Prioritization of the affected areas |  | DA-Province | 2020 Budget Reprogram and for Approval | Regular Funds | 2020
Distribution of livestock animals
carabao dispersal
| cattle |  |  | Livelihood assistance provided
| Vetenirary Medical Outreach program | All target LGUs
Medical Mission
| Rice, Corn and High Value Crops Program |  |  |  |  | 2020 Budget Reprogram and for Approval | Regular Funds | 2020
seed distrib+B10:B13ution
-rice
-corn
assorted vegetables
-planting materials
| Pest and Animal Surveillance Program |  |  |  |  | 2020 Budget Reprogram and for Approval | Regular Funds | 2020
Bantay Peste
| SAAD Program |  |  |  |  | 2020 Budget Reprogram and for Approval | Regular Funds | 2020
Food production and Livelihood Projects
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DSWD
Issues and Concerns to be Addressed | Program/Project/ Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Unincluded in the list of Listahanan Databased | Prioritize all target barangays (Influenced and Less Influenced) in the ongoing Listahan 3 enumeration | Canlaon City ( barangay: Bayog and Lumapao) | Note: This is for enumeration | Data based updated on all beneficiaries in the inclusion of Listahanan 3 survey | Listahanan, DSWD | Listahanan 3 Funds | Program Staff support | October to December 2019
Guijulngan City (barangays: Binobohan, Imelda, Hinakpan, Tacpao, Sandayao, Trinidad, Planas, Humayhumay)
Siaton (Barangay Tayak)
Sta. Cataliana (Barangays San Pedro
Valencia (Barangay Dobdob)
Zamboanguita (Barangays: Calango, Mayabon)
Lack of access to financial assistance for small enterprise | Sustainable Livelihood Program | Canlaon City ( barangay: Bayog) | 25 | Participants gained additional income for the family | SLP Program, DSWD | Financial Livelihood Grants Php 222,250.00 | > For LGU to provide livelihood worker to continuously monitor the project. | CY 2019 Ongoing
|  | Guihulngan: Brgy. Imelda | 30 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Hinakpan | 16 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Tacpao | 26 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Sandayao | 19 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Trinidad | 20 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Planas | 60 |  |  | Livelihood Grants Php590,000.00
|  | Brgy. Humayhumay | 30 |  |  | Livelihood Grants Php300,000.00
|  | Siaton: Brgy. Tayak | 91 |  |  | Livelihood Grants Php708,498.00.00
|  | Zamboanguita: Brgy. Calango | 30 |  |  | Livelihood Grants Php300,000.00
|  | Brgy. Mayabon | 93 |  |  | Livelihood Grants Php823,000,000.00
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN

## DEPED
Issues and Concerns to be Addressed | Program/ Project /Activity | Target Area | Target Beneficiaries | Expected Results/Outcome | Responsible Agency | Resources Needed | Support Needed | Duration | Remarks
(Funding)
Illiteracy | ALS Program | Canlaon City: Brgy. Bayog | Less Influenced Barangay |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Canlaon City: Brgy. Lumapao | Less Influenced Barangay |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Trinidad | Influenced Barangays | 102 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Binobohan | Influenced Barangays | 6 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Sandayao | Influenced Barangays | 79 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Tacpao | Influenced Barangays | 5 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Imelda | Influenced Barangays | 18 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Hinakpan | Influenced Barangays | 16 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Humayhumay | Less Influenced Barangay | 31 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Guihulngan City: Brgy. Planas | Less Influenced Barangay | 24 | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Valencia: Brgy. Dobdob | Less Influenced Barangay |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Santa Catalina: Brgy. San Pedro | Less Influenced Barangay |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Santa Catalina: Brgy. Talalak | Less Influenced Barangay |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Siaton: Brgy. Tayak | Influenced Barangays |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Zamboanguita: Brgy. Calango | Influenced Barangays |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
|  | Mun. Zamboanguita: Brgy. Mayabon | Influenced Barangays |  | Literate Individual | DepEd RO7 | Funding for additional mobile teachers | LGU | 2019 -2020
BASIC SERVICES CLUSTER IMPLEMENTATION PLAN